## Phase Overview
Workout PWA — Execution Plan
# | Phase Name | Goal / Focus | Output / Done-When | Status
1 | Project Setup | Running PWA shell installable on iPhone via Safari | App installs to iPhone home screen and loads offline | Not Started
2 | Movement Library | Data-driven movements with looping CSS animations | All movements display with working animations on the library screen | Not Started
3 | Routine Builder | Users can build, name, save, and manage routines | User can create, edit, save, and delete routines | Not Started
4 | Workout Player | Focused workout mode that guides user through a routine | User can start a routine and be guided through every movement | Not Started
5 | Milestones & Themes | Celebrate workout streaks with unlockable backgrounds | Milestone-triggering workout shows a celebration and unlocks new background | Not Started
6 | Daily Quote | Fresh motivational quote greets the user each day | Home screen shows a daily quote that changes each day | Not Started
7 | PWA Hardening | Reliable offline experience and smooth iOS installation | App works fully offline and feels native on iPhone | Not Started
8 | Polish & Testing | Smooth, enjoyable experience ready for daily use | App is stable, smooth, and ready for daily use on iPhone | Not Started

## Task Tracker
Workout PWA — Task Tracker
Ph | Phase Name | Task | Status | Priority | Notes
1 | Project Setup | Create GitHub repo | Not Started | Medium
1 | Project Setup | Scaffold file structure (index.html, style.css, app.js, manifest.json, sw.js) | Not Started | Medium
1 | Project Setup | Set up manifest.json with name, icons, display mode, theme colour | Not Started | Medium
1 | Project Setup | Register a basic service worker (cache shell on install) | Not Started | Medium
1 | Project Setup | Verify 'Add to Home Screen' works in Safari iOS | Not Started | Medium
1 | Project Setup | Set up CSS custom properties for theming (colours, fonts, spacing) | Not Started | Medium
1 | Project Setup | Build app shell layout: header, main content area, bottom nav | Not Started | Medium
2 | Movement Library | Define movement data structure in data/movements.js | Not Started | Medium
2 | Movement Library | Add initial movement set: Abs, Four-point rotation, Hip flexor, Plank hold + 4 more | Not Started | Medium
2 | Movement Library | Write CSS keyframe animation for each movement in animations/movements.css | Not Started | Medium
2 | Movement Library | Build a movement library screen listing all movements | Not Started | Medium
2 | Movement Library | Tapping a movement shows detail view (name, description, animation, default settings) | Not Started | Medium
3 | Routine Builder | Build routine list screen (home — shows saved routines) | Not Started | Medium
3 | Routine Builder | Build 'create routine' flow — name the routine | Not Started | Medium
3 | Routine Builder | Build 'create routine' flow — browse and select movements from library | Not Started | Medium
3 | Routine Builder | Build 'create routine' flow — set duration (seconds) and reps per movement | Not Started | Medium
3 | Routine Builder | Build 'create routine' flow — reorder movements (drag or up/down buttons) | Not Started | Medium
3 | Routine Builder | Build 'create routine' flow — remove movements | Not Started | Medium
3 | Routine Builder | Save routine to localStorage | Not Started | Medium
3 | Routine Builder | Edit and delete existing routines | Not Started | Medium
3 | Routine Builder | Validate: routine must have at least one movement before saving | Not Started | Medium
4 | Workout Player | Build workout player screen | Not Started | Medium
4 | Workout Player | Show current movement name, description, and animation (full-screen, minimal UI) | Not Started | Medium
4 | Workout Player | Implement countdown timer per set (configurable duration) | Not Started | Medium
4 | Workout Player | Show rep count and overall progress (e.g. 'Movement 2 of 5') | Not Started | Medium
4 | Workout Player | Auto-advance to next movement when timer reaches zero | Not Started | Medium
4 | Workout Player | Play audio cue on set end (Web Audio API — no external files) | Not Started | Medium
4 | Workout Player | Pause / resume control | Not Started | Medium
4 | Workout Player | Show completion screen when routine finishes | Not Started | Medium
4 | Workout Player | Increment totalWorkoutsCompleted in localStorage on completion | Not Started | Medium
5 | Milestones & Themes | Define milestone thresholds and corresponding background themes | Not Started | Medium
5 | Milestones & Themes | Check for new milestone on every workout completion | Not Started | Medium
5 | Milestones & Themes | Show milestone celebration screen (message + theme preview) | Not Started | Medium
5 | Milestones & Themes | Persist unlocked milestones and active background in localStorage | Not Started | Medium
5 | Milestones & Themes | Apply active background theme to app shell via CSS custom properties | Not Started | Medium
5 | Milestones & Themes | Build achievements view showing locked and unlocked milestones | Not Started | Medium
6 | Daily Quote | Write a curated list of 60+ quotes in data/quotes.js | Not Started | Medium
6 | Daily Quote | Implement date-based quote selection (same quote all day, changes at midnight) | Not Started | Medium
6 | Daily Quote | Display quote prominently on home / routine list screen | Not Started | Medium
6 | Daily Quote | No external API — fully offline | Not Started | Medium
7 | PWA Hardening | Implement cache-first service worker strategy for all app assets | Not Started | Medium
7 | PWA Hardening | Pre-cache all HTML, CSS, JS, and animation files on install | Not Started | Medium
7 | PWA Hardening | Handle service worker updates gracefully (notify user, refresh) | Not Started | Medium
7 | PWA Hardening | Verify full offline functionality (no network required after first load) | Not Started | Medium
7 | PWA Hardening | Add iOS-specific meta tags (apple-mobile-web-app-capable, status bar, splash screens) | Not Started | Medium
7 | PWA Hardening | Test install and launch from iPhone home screen in Safari | Not Started | Medium
7 | PWA Hardening | Prevent scroll bounce and ensure full-screen feel on iOS | Not Started | Medium
8 | Polish & Testing | Test all flows on iPhone (Safari, installed PWA mode) | Not Started | Medium
8 | Polish & Testing | Test on at least two iOS versions | Not Started | Medium
8 | Polish & Testing | Accessibility: sufficient colour contrast, tap target sizes ≥ 44px | Not Started | Medium
8 | Polish & Testing | Keyboard / focus management in modals and player | Not Started | Medium
8 | Polish & Testing | Performance: animations run at 60fps, no jank during timer | Not Started | Medium
8 | Polish & Testing | Edge cases: empty routine list, single-movement routine, back button during workout | Not Started | Medium
8 | Polish & Testing | Add subtle transition animations between screens | Not Started | Medium
8 | Polish & Testing | Final UX review: icon, splash screen, colour themes | Not Started | Medium

## Tech Decisions
Key Technical Decisions
Decision | Choice | Reason
Framework | None (vanilla JS) | Zero build tooling, easier PWA
Animations | CSS keyframes | Performant, no dependencies
Storage | localStorage | Simple, offline, no backend
Audio | Web Audio API | No external files, works offline
Routing | Hash-based (#routines…) | No server needed
Icons | Self-hosted PNG | No CDN dependency